## Documents Management
DOCUMENT REGISTER — Reverse Pump Energy Recovery PLM
Program | Underground pressure-reducing stations / reverse pump-as-turbine generation | Lifecycle | Project Proposal → Design → Validation & Testing → Commissioning → O&M | As of | 2015-09-21 | Owner | PLM / Configuration Mgmt
Governance | Owned full lifecycle delivery under stage-gate control | Reporting | KPI-driven technical + financial + operational cadence | Cadence | Monthly ops / quarterly steering
TC Document ID | Revision | Stage | Document Type | Controlled Deliverable | Owner | Release State | Release Date
TC-DOC-0001 | A | Project Proposal | Business Case | Initial 2012 proposal for energy recovery at underground pressure stations | PMO | Released | 2012-03-15
TC-DOC-0002 | B | Project Proposal | Feasibility | 14-station candidate screening, hydraulic map and spatial constraints | Hydraulics | Released | 2012-08-30
TC-DOC-0003 | C | Project Proposal | Financial Model | Target EPC CapEx $14.0M, payback 5.0 years, IRR 10–13% | Finance | Released | 2012-12-20
TC-DOC-0101 | A | Design | System Requirements | PAT/turbine, generator, bypass valve, MCC, relay protection and SCADA requirements | Systems Eng. | Released | 2013-04-18
TC-DOC-0102 | B | Design | EBOM Baseline | Engineering BOM for hydraulic skid, electrical package and instrumentation | PLM Admin | Released | 2013-11-22
TC-DOC-0103 | B | Design | Interface Control | Mechanical, electrical, civil and SCADA interface control document | Systems Eng. | Released | 2014-02-14
TC-DOC-0104 | C | Design | HAZOP / LOPA | HAZOP actions for bypass isolation, overspeed, flooding and LOTO | HSE | Released | 2014-09-05
TC-DOC-0201 | A | Validation & Testing | DVP&R | Hydraulic duty, vibration, protection trip and bypass validation plan | Validation | Released | 2015-01-23
TC-DOC-0202 | A | Validation & Testing | Factory Test | Generator, MCC, protection relay and FAT acceptance record | Electrical | Released | 2015-05-29
TC-DOC-0203 | B | Validation & Testing | Pilot Report | 0.25 MW pilot, $0.75M CapEx, 18-month development close-out | PMO | Released | 2015-09-30
TC-DOC-0301 | A | Commissioning | Method Statement | Wet commissioning, grid synchronization and trip-test protocol | Commissioning | Released | 2016-02-19
TC-DOC-0302 | A | Commissioning | As-Built Pack | As-built drawings, cable schedules, valve datasheets and PLC backups | Site Eng. | Released | 2016-07-28
TC-DOC-0401 | A | O&M | Maintenance Plan | Monthly inspections, quarterly vibration review, annual relay test and spares | O&M | Released | 2017-01-31
TC-DOC-0402 | B | O&M | KPI Pack | Uptime 96–99%, net generation, downtime causes and economics dashboard | Operations | Released | 2018-06-29
TC-DOC-0403 | A | O&M | Failure Review | Decommissioned station field attrition report and corrective-action feedback | Reliability | Released | 2019-03-22
TC-DOC-0404 | C | O&M | Steering Report | Quarterly steering committee report with stage-gate escalation paths | PMO | Released | 2020-12-18
TC-DOC-0405 | B | O&M | Lifecycle Cost Review | OPEX, spares, overhaul reserve and net cash-flow refresh | Finance | Released | 2023-11-10
TC-DOC-0406 | A | O&M | NPI Lessons Learned | 14 candidates, 2 filtered, 1 field decommissioned, 11 operating | PMO | Released | 2024-10-04
TC-DOC-0407 | A | O&M | PLM Data Dictionary | Teamcenter item/revision/ECN/status definitions for refresh control | PLM Admin | Released | 2026-06-10

## BOM Management (EBOM_MBOM)
EBOM → MBOM BASELINE — Pump-as-Turbine / Generator Skid
Item ID | Rev | System | EBOM Qty | MBOM Qty | Make/Buy | Supplier / Work Center | Unit Cost $k | Lifecycle State | Change Ref
PAT-ASSY-250KW | C | Hydraulic Turbine Package | 1 | 1 | Buy | PAT OEM / Hydraulics | 310 | Released | ECN-014
GEN-ASSY-480V | B | Generator | 1 | 1 | Buy | Generator OEM | 185 | Released | ECN-008
SKID-FRAME-SS | B | Mechanical Skid | 1 | 1 | Make | Fabrication Shop | 95 | Released | ECN-006
BYP-VLV-MOD | C | Bypass / Isolation Valves | 3 | 3 | Buy | Valve OEM | 72 | Released | ECN-009
PIPE-SPOOL-SS316 | C | Pipe Spools | 6 | 7 | Make | Fabrication Shop | 54 | Released | ECN-006
MCC-PNL-480V | B | Electrical MCC | 1 | 1 | Buy | Panel Builder | 140 | Released | ECN-008
REL-PROT-GRID | B | Protection Relay | 1 | 1 | Buy | Protection OEM | 38 | Released | ECN-008
SCADA-PLC-IO | C | Controls / SCADA | 1 | 1 | Buy | Controls Integrator | 112 | Released | ECN-011
METER-REV-ANSI | B | Revenue Metering | 1 | 1 | Buy | Meter OEM | 24 | Released | ECN-011
VFD-BRAKE-OPT | A | Power Electronics | 1 | 1 | Buy | Drive OEM | 78 | Released | ECN-010
INS-VIB-TEMP | B | Instrumentation | 1 | 1 | Buy | Instrumentation Supplier | 31 | Released | ECN-012
CIVIL-ANCHOR-KIT | A | Civil / Anchors | 1 | 1 | Make | Civil Contractor | 44 | Released | ECN-005
FAT-SAT-PKG | A | Validation Services | 1 | 1 | Service | Test Vendor | 65 | Released | ECN-013
SPARES-YR1-KIT | A | O&M Spares | 1 | 1 | Buy | O&M Stores | 26 | Released | ECN-015
DOC-ASBUILT-PKG | A | Documentation | 1 | 1 | Make | Site Engineering | 18 | Released | ECN-016
CYBER-HIST-NODE | A | SCADA Historian | 1 | 1 | Buy | Controls Integrator | 42 | Released | ECN-017
HOIST-ACCESS-KIT | B | Maintenance Access | 1 | 1 | Buy | Lifting Supplier | 29 | Released | ECN-007
DRAIN-SUMP-MOD | A | Flood Protection | 1 | 1 | Make | Civil Contractor | 36 | Released | ECN-018
NOISE-ENCLOSURE | A | Acoustic / Safety | 1 | 1 | Buy | Acoustic Supplier | 22 | Released | ECN-019
TRAINING-OPS-PKG | A | O&M Training | 1 | 1 | Service | O&M Lead | 14 | Released | ECN-020
OVERHAUL-RESERVE | A | Lifecycle Reserve | 1 | 1 | Service | Finance / O&M | 30 | Planning | ECN-021
SITE-SURVEY-PKG | B | Engineering Services | 1 | 1 | Service | Hydraulic Survey Team | 55 | Released | ECN-003
GRID-STUDY-PKG | B | Interconnection | 1 | 1 | Service | Electrical Consultant | 48 | Released | ECN-004
QA-DOSSIER-PKG | A | Quality Dossier | 1 | 1 | Make | Quality | 12 | Released | ECN-013
PLM-CONFIG-PKG | A | PLM Configuration | 1 | 1 | Service | PLM Admin | 16 | Released | ECN-001
|  | Summary | Formula | Unit | Status
|  | Total reference MBOM unit cost | 1596 | $k / station package | OK
|  | Qty mismatch count | 1 | count | Review pipe spool planned extra

## Change Management (Change_Log)
Change Log
Change ID | Date | Stage | ECR / ECO Type | Description | Affected System | Priority | Time Impact | CapEx Impact $k | OPEX Impact $k/yr | Disposition | Owner | KPI | Value | Status
CHG-001 | 2012-02-20 | Project Proposal | Scope Baseline | Create PLM baseline for reverse pump energy recovery opportunity | Program | High | +10 days | 45 | 0 | Accepted | PMO | Total changes | 24 | OK
CHG-002 | 2012-05-14 | Project Proposal | Feasibility | Add 14-station hydraulic survey and pressure head capture | Hydraulics | Critical | +30 days | 120 | 0 | Accepted | Hydraulics | Accepted / closed | 24 | OK
CHG-003 | 2012-09-07 | Project Proposal | Financial | Add EPC target CapEx $14M and hurdle payback/IRR controls | Finance | High | +5 days | 0 | 0 | Accepted | Finance | Critical changes | 8 | Watch
CHG-004 | 2013-04-26 | Design | Requirements | Split sites by Group A/B and define station-level KPI schema | Systems | Medium | +5 days | 10 | 0 | Accepted | Controls | CapEx impact $k | 945 | Tie to CBA
CHG-005 | 2013-11-22 | Design | EBOM | Expand EBOM for PAT, generator, bypass valves, pipe spools and controls | Mechanical / Electrical | High | +20 days | 85 | 0 | Accepted | PLM Admin | Annual OPEX impact $k | 78 | Tie to CBA
CHG-006 | 2013-09-13 | Design | Civil | Eliminate ST-07 due severe access and physical space constraints | Civil / Site | Critical | -1 station | 0 | 0 | Rejected from scope | Civil | External link remediation | 0 | PASS
CHG-007 | 2014-02-03 | Design | Materials | Revise pipe spool material to SS316 after corrosion review | Mechanical | High | +12 days | 55 | 8 | Accepted | Mechanical
CHG-008 | 2014-06-24 | Design | Electrical | Add MCC/protection relay package and grid interconnection study | Electrical | Critical | +25 days | 160 | 5 | Accepted | Electrical
CHG-009 | 2014-10-13 | Design | Feasibility | Eliminate ST-12 due installation risk and confined-space conflict | Site Engineering | Critical | -1 station | 0 | 0 | Rejected from scope | Site Eng.
CHG-010 | 2015-01-23 | Validation & Testing | DVP&R | Add overspeed trip, vibration acceptance and hydraulic duty-point testing | Validation | High | +18 days | 40 | 3 | Accepted | Validation
CHG-011 | 2015-05-29 | Validation & Testing | Controls | Add SCADA, revenue metering and historian integration requirements | Controls | High | +18 days | 95 | 12 | Accepted | Controls
CHG-012 | 2015-09-30 | Validation & Testing | Pilot Closeout | Close 0.25 MW pilot after 18-month development and update lessons learned | Pilot | High | 0 days | 0 | 0 | Accepted | PMO
CHG-013 | 2016-02-19 | Commissioning | HSE | Add HAZOP/LOTO actions before commissioning release | HSE | Critical | +20 days | 40 | 4 | Accepted | HSE
CHG-014 | 2016-07-28 | Commissioning | Procurement | Finalize PAT package quotes and release construction MBOM | Procurement | Critical | +15 days | 210 | 0 | Accepted | Procurement
CHG-015 | 2017-01-31 | O&M | Spares | Add O&M spare kit and operator training deliverables | O&M | Medium | +8 days | 35 | 18 | Accepted | O&M
CHG-016 | 2018-06-29 | O&M | KPI Reporting | Establish uptime, generation, downtime-cause and financial KPI dashboard | Operations | High | +5 days | 18 | 7 | Accepted | Operations
CHG-017 | 2019-03-22 | O&M | Field Attrition | Decommission ST-09 after repeated bearing/vibration failures; return failure data to PLM | Reliability | Critical | -1 station | 0 | -18 | Closed with lessons | Reliability
CHG-018 | 2020-12-18 | O&M | Governance | Formalize monthly operating review and quarterly steering escalation path | PMO | High | 0 days | 0 | 0 | Accepted | PMO
CHG-019 | 2021-08-20 | O&M | Cyber / Data | Add SCADA historian naming standard and data retention controls | Controls | Medium | +4 days | 12 | 5 | Accepted | Controls
CHG-020 | 2022-04-15 | O&M | Reliability | Add vibration trending alarms and quarterly condition-monitoring review | Reliability | High | 0 days | 20 | 9 | Accepted | Reliability
CHG-021 | 2023-11-10 | O&M | Finance | Refresh OPEX, reserve and net cash-flow economics against target $14M CapEx | Finance | High | 0 days | 0 | 0 | Accepted | Finance
CHG-022 | 2024-10-04 | O&M | NPI Feedback | Add attrition summary: 14 candidates, 2 filtered, 1 field attrition, 11 operating | PMO | High | 0 days | 0 | 0 | Accepted | PMO
CHG-023 | 2025-06-27 | O&M | Overhaul | Schedule generator bearing inspection and PAT wear-part overhaul cycle | O&M | Medium | 0 days | 0 | 25 | Accepted | O&M
CHG-024 | 2026-06-10 | O&M | Report Refresh | Refresh executive report and remove unresolved external workbook link prompt | PLM / Finance | Critical | 0 days | 0 | 0 | Accepted | PLM Admin

## Change Management (ECN)
ECN | 2012-05-14 | CHG-002 | SITE-SURVEY-PKG / B | Project Proposal | Need station-level hydraulic head and flow data | Survey template released | Development budget added | G1 | Hydraulics | PMO | 120 | 0 | High | Medium | Released | B
ECN-001 | 2013-09-13 | CHG-006 | ST-07 Site Record | Design | Physical envelope incompatible with skid and safe access | Station removed before execution | Avoided stranded CapEx | G1 | Civil | Steering | 0 | 0 | Very High | Closed | Released | N/A
ECN-003 | 2014-02-03 | CHG-007 | PIPE-SPOOL-SS316 / C | Design | Corrosion risk under condensate and washdown exposure | SS316 spool material released | CapEx +$55k; OPEX +$8k/yr | G2 | Mechanical | HSE | 55 | 8 | High | Low | Released | C
ECN-005 | 2014-06-24 | CHG-008 | MCC-PNL-480V / B | Design | Protection and synchronization requirements incomplete | MCC/protection panel released | Included in EPC target | G2 | Electrical | Quality | 160 | 5 | High | Medium | Released | B
ECN-006 | 2014-10-13 | CHG-009 | ST-12 Site Record | Design | Confined-space and installation risk exceeds threshold | Station removed before execution | Avoided high-risk spend | G1 | Site Eng. | Steering | 0 | 0 | Very High | Closed | Released | N/A
ECN-008 | 2015-01-23 | CHG-010 | VFD-BRAKE-OPT / A | Validation & Testing | Overspeed and transient trip testing identified braking requirement | Braking option released | CapEx +$40k | G3 | Validation | Electrical | 40 | 3 | High | Medium | Released | A
ECN-007 | 2015-05-29 | CHG-011 | SCADA-PLC-IO / C | Validation & Testing | Remote monitoring and revenue reporting require historian data | SCADA/historian scope released | OPEX data capture improves reporting | G3 | Controls | Operations | 95 | 12 | Medium | Low | Released | C
ECN-010 | 2016-02-19 | CHG-013 | FAT-SAT-PKG / A | Commissioning | Safety and test evidence needed before wet commissioning | FAT/SAT dossier mandatory | CapEx +$40k | G4 | HSE | Quality | 40 | 4 | High | Low | Released | A
ECN-011 | 2016-07-28 | CHG-014 | PAT-ASSY-250KW / C | Commissioning | Supplier final quote package and PAT curves received | PAT package released | CapEx +$210k | G4 | Procurement | Engineering | 210 | 0 | Medium | Low | Released | C
ECN-013 | 2017-01-31 | CHG-015 | SPARES-YR1-KIT / A | O&M | Initial operating period needs spare bearings, seals, sensors | Spares kit and training released | CapEx +$35k; OPEX +$18k/yr | G5 | O&M | Finance | 35 | 18 | Medium | Low | Released | A
ECN-014 | 2017-01-31 | CHG-017 | ST-09 Site Record | O&M | Repeated bearing/vibration failures after installation | Station decommissioned; DVP&R updated | Reduced future OPEX drag | G5 | Reliability | Steering | 0 | -18 | Very High | Closed | Released | N/A
ECN-015 | 2017-01-31 | CHG-021 | OVERHAUL-RESERVE / A | O&M | Lifecycle reserve needed for overhaul and major maintenance | Annual reserve added to economics | Net cash-flow adjusted for IRR | G5 | Finance | O&M | 0 | 300 | Medium | Low | Released | A
ECN-017 | 2017-01-31 | CHG-024 | Workbook Linkage / A | O&M | Workbook opened with update-link prompt; model should be self-contained | Break external workbook links and rebuild local formulas | No financial impact | G5 | PLM Admin | Finance | 0 | 0 | High | Low | Released | A
ECN-021 | 2017-01-31 | CHG-024 | Executive Pack / D | O&M | Steering pack needed full technical and financial refresh | Dashboard and executive report rebuilt | Reporting improvement | G5 | PMO | Steering | 0 | 0 | Medium | Low | Released | D
ECN-024
ECN-025

## Validation & Release Management
VALIDATION & RELEASE MANAGEMENT
Gate | Stage | Target Date | Exit Criteria | Technical Evidence | Financial Evidence | Operational Evidence | Decision | Escalation Path | Owner
G0 | Project Proposal | 2012-03-15 | Opportunity defined and PLM baseline opened | Pressure energy recovery concept note | Initial EPC budget | NPI charter | Pass | PMO → Steering | PMO
G1 | Feasibility Filtering | 2012-12-20 | 14 candidates screened; unsafe sites removed | Hydraulic survey and envelope checks | Pilot $0.75M / 0.25MW / 18 months approved | Site access risk review | Pass with attrition | Engineering → Steering | Hydraulics
G2 | Design Freeze | 2014-10-13 | EBOM, interfaces, HAZOP and grid study released | PAT curves, generator sizing, protection settings | CapEx bridge within $14M target | Procurement readiness | Pass | Design Authority | Systems Eng.
G3 | Validation & Testing | 2015-09-30 | DVP&R and pilot close-out accepted | FAT, SAT, overspeed, vibration, thermal tests | Pilot learnings incorporated | Operator training plan | Pass | Validation Board | Validation
G4 | Commissioning | 2016-07-28 | Wet commissioning and grid sync evidence complete | Trip tests, bypass operation, SCADA points | Installed cost and forecast OPEX refreshed | Site handover | Pass | Commissioning Board | Commissioning
G5 | O&M Release | 2016-01-31 | 11 operating stations transitioned to KPI governance | Reliability alarms, historian data, maintenance plan | Payback / IRR tracked monthly/quarterly | Monthly ops review | Pass / monitor | Operations → Steering | O&M
G5-FB | Field Attrition Feedback | 2017-03-22 | ST-09 decommissioned and lessons pushed to PLM | Bearing/vibration failure data attached to DVP&R | OPEX risk reduced after removal | Corrective actions closed | Closed with lessons | Reliability Board | Reliability
Validation Test ID | System | Acceptance Criteria | Coverage | Result | Defect Count | Corrective Action | Release Impact | Owner | Status
VAL-001 | Hydraulic PAT | Duty point within ±5% of curve | Pilot + 11 active stations | Pass | 0 | None | Release | Hydraulics | Closed
VAL-002 | Generator | Temperature rise within OEM class | FAT all generator packages | Pass | 1 | Cooling airflow note added | Release | Electrical | Closed
VAL-003 | Protection Relay | Trip selectivity and anti-islanding verified | All commissioned stations | Pass | 0 | None | Release | Electrical | Closed
VAL-004 | Bypass Valve | Fail-safe bypass open on trip/loss of power | All commissioned stations | Pass | 2 | Valve actuator setting revised | Release after CA | Mechanical | Closed
VAL-005 | Vibration | RMS vibration below alarm limit | Pilot and operating stations | Pass with monitor | 1 | Quarterly vibration trend | Monitor | Reliability | Open monitor
VAL-006 | SCADA Historian | Revenue and downtime tags captured | 11 operating stations | Pass | 0 | None | Release | Controls | Closed
VAL-007 | HAZOP / LOTO | All category A actions closed before wet commissioning | All stations | Pass | 0 | None | Release | HSE | Closed
VAL-008 | Civil Access | Safe maintenance envelope and lifting plan | 14 candidates | Fail for 2 | 2 | Remove ST-07/ST-12 | Scope attrition | Civil | Closed
VAL-009 | Commercial Case | Payback ≤5 years and IRR 10–13% | Portfolio case | Pass | 0 | Refresh quarterly | Steering report | Finance | Closed
VAL-010 | Uptime KPI | Operating uptime in 96–99% band | Monthly O&M data | Pass | 0 | Escalate if <96% | O&M release | Operations | Live
VAL-011 | Cyber / OT | Historian naming and OT access control implemented | 11 stations | Pass | 0 | Annual access review | O&M release | IT/OT | Live
VAL-012 | Failure Feedback | Field failure lessons fed into PLM and DVP&R | ST-09 | Pass | 0 | DVP&R updated | Closed loop | Reliability | Closed
VAL-013 | Financial Controls | No external links and local formulas for steering pack | Workbook | Pass | 0 | Break links / local rebuild | Release | Finance | Closed
VAL-014 | Stage-Gate Traceability | Each gate has technical, financial and operating evidence | All gates | Pass | 0 | Quarterly audit | Governance | PMO | Live

## Risk Management
RISK MANAGEMENT + NPI ATTRITION - 14 candidate stations to 11 operating assets
Station | Group | Stage Outcome | Commissioned | Operating Status | Capacity MW | Uptime % | Annual GWh | CapEx M$ | Key Constraint / Failure Mode | Tech Gate | Finance Gate | Ops Gate | Residual Risk | PLM Feedback
ST-01 | A | Operating | 2016-05-20 | Active | 0.26 | 0.982 | 2.2366 | 1.24 | Normal PRV replacement envelope | Pass | Pass | Pass | Low | Baseline retained
ST-02 | A | Operating | 2016-06-10 | Active | 0.24 | 0.976 | 2.0519 | 1.18 | High moisture controlled by enclosure | Pass | Pass | Pass | Low | Maintenance note
ST-03 | A | Operating | 2016-07-08 | Active | 0.25 | 0.989 | 2.1659 | 1.25 | Noise abatement required | Pass | Pass | Pass | Low | Acoustic kit added
ST-04 | A | Operating | 2016-08-12 | Active | 0.28 | 0.971 | 2.3817 | 1.3 | Civil anchors upgraded | Pass | Pass | Pass | Medium | Anchor kit standard
ST-05 | A | Operating | 2016-09-16 | Active | 0.23 | 0.968 | 1.9503 | 1.16 | Valve actuator tuning | Pass | Pass | Pass | Medium | Valve setting CA
ST-06 | A | Operating | 2016-10-14 | Active | 0.25 | 0.981 | 2.1484 | 1.22 | SCADA tag mapping | Pass | Pass | Pass | Low | Historian standard
ST-07 | A | Filtered out | N/A | Eliminated pre-execution | 0 | 0 | 0 | 0 | Severe physical space and safe access constraint | Fail | N/A | N/A | Closed | Pre-execution elimination
ST-08 | B | Operating | 2016-11-18 | Active | 0.27 | 0.963 | 2.2777 | 1.29 | Bypass valve access conflict resolved | Pass | Pass | Pass | Medium | Access kit added
ST-09 | B | Field attrition | 2017-01-20 | Decommissioned | 0.25 | 0 | 0 | 1.08 | Bearing/vibration failures under transient duty | Pass | Pass | Fail | Closed | Failure data to DVP&R
ST-10 | B | Operating | 2017-02-17 | Active | 0.24 | 0.974 | 2.0477 | 1.21 | Protection relay settings revised | Pass | Pass | Pass | Low | Relay template updated
ST-11 | B | Operating | 2017-03-17 | Active | 0.26 | 0.966 | 2.2002 | 1.26 | Condensate corrosion risk mitigated | Pass | Pass | Pass | Medium | SS316 standard
ST-12 | B | Filtered out | N/A | Eliminated pre-execution | 0 | 0 | 0 | 0 | Installation risk / confined space unacceptable | Fail | N/A | N/A | Closed | Pre-execution elimination
ST-13 | B | Operating | 2017-04-21 | Active | 0.24 | 0.986 | 2.073 | 1.2 | Grid interconnection study required | Pass | Pass | Pass | Low | Grid study template
ST-14 | B | Operating | 2017-05-19 | Active | 0.23 | 0.979 | 1.9725 | 1.19 | Operator access training required | Pass | Pass | Pass | Low | Training package
Risk ID | Category | Risk Event | Probability | Impact | Rating | Mitigation / Control | Status |  | Attrition Metric | Count | Formula / Trace | Status
R-001 | Hydraulic | Duty point drift reduces PAT output | Medium | High | High | Quarterly duty point review and curve revalidation | Monitored |  | Candidates entering NPI | 14 | User-provided project funnel | OK
R-002 | Mechanical | Bearing vibration exceeds alarm limit | Medium | High | High | Vibration sensors, inspection and overhaul reserve | Monitored |  | Filtered before execution | 2 | ST-07 + ST-12 | OK
R-003 | Electrical | Relay coordination or anti-islanding failure | Low | High | Medium | Annual relay test and grid study template | Controlled |  | Installed / commissioned | 12 | Candidates - filtered | OK
R-004 | Civil | No safe maintenance access | Low | High | Medium | Gate G1 envelope review; eliminated ST-07/ST-12 | Closed |  | Decommissioned after deployment | 1 | ST-09 | Closed
R-005 | Controls | SCADA data gaps impact revenue reporting | Low | Medium | Low | Historian tag standard and monthly data QC | Controlled |  | Operating today | 11 | Formula count | PASS
R-006 | Financial | CapEx exceeds $14M target | Low | High | Medium | ECN approval threshold and quarterly steering review | Controlled |  | Operating target | 11 | User requirement | PASS
R-007 | Financial | OPEX erodes 5-year payback | Medium | Medium | Medium | OPEX dashboard and lifecycle reserve | Monitored |  | Operating tie-out | 0 | 0 = PASS | PASS
R-008 | Operations | Uptime below 96% threshold | Low | High | Medium | Monthly O&M review with escalation below threshold | Controlled
R-009 | HSE | LOTO or bypass procedure not followed | Low | Very High | Medium | HAZOP/LOTO closure and annual training | Controlled
R-010 | Procurement | PAT or generator lead time delays commissioning | Medium | Medium | Medium | Supplier quote package and long-lead tracker | Closed
R-011 | Reliability | Field attrition repeats after ST-09 failure | Low | High | Medium | Failure mode added to DVP&R and design standard | Controlled
R-012 | Data | External workbook link corrupts steering report refresh | Low | Medium | Low | Local formulas and external link break completed | Closed
R-013 | Cyber / OT | Historian access not governed | Low | High | Medium | OT access review and historian naming governance | Controlled
R-014 | Commercial | Tariff sensitivity reduces IRR below hurdle | Medium | High | High | Quarterly sensitivity review and operating cost control | Monitored
R-015 | Environmental | Flooding or drainage event damages skid | Low | High | Medium | Drain/sump mod and inspection checklist | Controlled
R-016 | Quality | As-built records not synchronized to PLM | Low | Medium | Low | Quality dossier and PLM release checklist | Controlled
Project Risk |  | Related Stakeholders |  | Date | [9 empty] | Likelihood: Chance of risk
Rare: Slim possibility of happening
Unlikely: Could occur but remote
Possible: Might happen
Likely: Expected to occur
Almost Certain: Expected regularly
Risk Matrix |  | Severity
Severity: Impact on project
|  | Insignificant |  | Minor |  | Moderate |  | Major |  | Severe+K10:P21 |  |  |  | Insignificant: Not worth worry about
Minor: Can cause delays or added costs
Likelihood | Almost Certain | Medium |  | High |  | Very High |  | Very High |  | Very High |  |  |  | Moderate: Likely delays or costs
Major: Possible failure
Severe: Definite failure
Risk Level: Setting Priority
| Likely | Medium |  | High |  | High |  | Very High |  | Very High |  |  |  | Low: Not much risk
Medium: Some risk
High: Major risk
Very High: Extreme risk
| Possible | Low |  | Medium |  | High |  | High |  | Very High
| Unlikelyh | Low |  | Low |  | Medium |  | Medium |  | High
| Rare | Low |  | Low |  | Low |  | Low |  | Medium

## Cost Benefit Analysis
COST-BENEFIT ANALYSIS: CAPEX, OPEX, ROI & IRR |  |  | PROJECT: Multi-Site Pressure Reducing & Power Generation
Input / Output | Value | Unit | Type | Source / Notes | Status
Target EPC CapEx | 14 | M$ | Input | User-provided target EPC CapEx | OK
Target Payback | 5 | years | Input | User-provided target payback | OK
Target IRR Low | 0.1 | % | Input | User-provided lower hurdle | OK
Target IRR High | 0.13 | % | Input | User-provided upper hurdle | OK
Pilot CapEx | 0.75 | M$ | Input | 0.25 MW pilot program | OK
Pilot Capacity | 0.25 | MW | Input | Pilot capacity | OK
Pilot Development Duration | 18 | months | Input | Development duration | OK
Candidate Stations | 14 | count | Input | NPI candidate funnel | OK
Eliminated Pre-Execution | 2 | count | Input | Site risk / space constraints | OK
Decommissioned Post-Install | 1 | count | Input | ST-09 field attrition | OK
Operating Stations | 11 | count | Formula | 14 candidates - 2 filtered - 1 decommissioned | PASS
Avg Capacity per Operating Station | 0.25 | MW | Input | PAT package design basis | OK
Operating Uptime / Availability | 0.975 | % | Input | Within 96–99% uptime KPI band | OK
Blended Revenue Tariff | 0.175 | $/kWh | Input | Commercial assumption; M$/GWh equivalent | OK
Fixed O&M | 0.649 | M$/yr | Input | Staffing, inspections, insurance, compliance | OK
Variable O&M Rate | 0.02815 | M$/GWh | Input | Wear parts, spares, condition monitoring | OK
Economic Output | Value | Unit | Formula / Logic | Target / Threshold | Status
Installed Operating Capacity | 2.75 | MW | Operating stations × 0.25 MW | n/a | OK
Annual Net Generation | 23.4877 | GWh/yr | Capacity × hours × uptime | n/a | OK
Gross Revenue | 4.1104 | M$/yr | GWh × $/kWh | n/a | OK
Variable O&M | 0.66118 | M$/yr | GWh × variable O&M rate | n/a | OK
Total OPEX | 1.3102 | M$/yr | Fixed + variable O&M | n/a | OK
EBITDA before Reserve | 2.8002 | M$/yr | Gross revenue - total OPEX | n/a | OK
Simple Payback | 4.9997 | years | Target EPC CapEx / EBITDA | ≤ 5.0 | PASS
Lifecycle Reserve | 0.3 | M$/yr | Major overhaul reserve | n/a | OK
Annual Net Operating Cash Flow | 2.5002 | M$/yr | EBITDA less lifecycle reserve | n/a | OK
Project IRR | 11.75% | % | 10-year unlevered cash flow incl. ramp/residual | 10–13% | PASS
IRR Hurdle Check | PASS | status | Within user-provided range | 10–13% | PASS
Payback Check | PASS | status | Simple payback vs target | ≤ 5.0 years | PASS
Cash Flow Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Unlevered FCF M$ | -14 | 2.1251 | 2.3752 | 2.5002 | 2.5002 | 2.5002 | 2.5002 | 2.5002 | 2.5002 | 2.5002 | 3.0002
Sensitivity | Downside | Base | Upside | Notes | Status
Tariff $/kWh | 0.155 | 0.175 | 0.195 | Commercial revenue sensitivity | Monitor
Availability | 0.96 | 0.975 | 0.99 | Uptime KPI range | PASS
EBITDA M$/yr | 2.2846 | 2.8002 | 3.3302 | Directional sensitivity | OK
Payback yrs | 6.128 | 4.9997 | 4.2039 | Lower is better | OK
Steering cadence | Monthly ops | Quarterly steering | Escalate below 96% uptime | Governance rule | Live
Note on B18: Mehrnia, Seyedmajid: Assumption: Fixed annual O&M calibrated to maintain user-provided ~5.0-year payback target while retaining detailed OPEX model ¦ Date: 2026-06-10

## Dashboard
EXECUTIVE DASHBOARD: Multi-Site Pressure Reducing & Power Generation PLM Portfolio
KPI | Value | Unit | Target / Band | Status | Interpretation | KPI | Value | Unit | Status
Target EPC CapEx | 14 | M$ | $14.0M | PASS | Portfolio tied to EPC target | Operating stations | 11 | count | PASS
Simple Payback | 4.9997 | years | ≤5.0 | PASS | Meets user hurdle before financing | Project IRR | 11.75% | % | PASS
Annual Generation | 23.4877 | GWh/yr | n/a | OK | 11 active stations at 97.5% availability | Uptime KPI | 0.975 | % | PASS
Gross Revenue | 4.1104 | M$/yr | n/a | OK | Tariff-linked energy recovery revenue | OPEX | 1.3102 | M$/yr | OK
Candidate Stations | 14 | count | 14 | OK | NPI funnel entry count | Filtered | 2 | count | OK
Installed / Commissioned | 12 | count | 12 | OK | One installed station decommissioned | Decommissioned | 1 | count | Closed
Steering Cadence | Monthly / Quarterly | cadence | Ops / Steering | Live | Monthly KPI review; quarterly steering | Link Prompt | Removed / local formulas | status | PASS
Lifecycle Stage | Gate | Start | Finish / Release | Status | Main Evidence |  | Attrition Funnel | Stations | Notes
Project Proposal | G0 | 2012-01 | 2012-03 | Complete | PLM baseline + business case |  | Candidate stations | 14 | NPI entry
Pre-Execution Feasibility | G1 | 2012-04 | 2012-12 | Complete | 14 candidates screened; 2 removed |  | Pre-execution eliminated | 2 | ST-07/ST-12
Design | G2 | 2013-01 | 2014-10 | Complete | EBOM/MBOM, HAZOP, grid study |  | Installed / commissioned | 12 | After feasibility
Validation & Testing | G3 | 2014-11 | 2015-09 | Complete | Pilot, FAT/SAT, DVP&R |  | Post-install decommissioned | 1 | ST-09
Commissioning | G4 | 2015-10 | 2016-07 | Complete | Wet commissioning + grid sync |  | Operating today | 11 | Active assets
O&M | G5 | 2017-01 | Present | Live | 11 operating stations; KPI governance
Field Feedback | G5-FB | 2019-03 | Closed | Closed | ST-09 failure data fed back to PLM
Management Takeaway | Detail | Owner | Cadence | Escalation Trigger | Status | Evidence Sheet | Cell / Range | Next Action | Due
Economic case meets hurdle | Payback near 5 years and IRR in 10–13% band | Finance | Quarterly | IRR <10% or payback >5.0 | PASS | Cost Benefit Analysis | A21:F36 | Maintain OPEX and uptime discipline | 2026-Q3
Technical envelope stable | 11 operating stations have accepted release evidence | Systems Eng. | Monthly | Any uptime <96% | PASS | Validation & Release Management | A12:J26 | Continue vibration trend review | Monthly
Attrition captured correctly | 14 candidates, 2 pre-execution filters, 1 decommissioned, 11 active | PMO | Quarterly | Uncontrolled field attrition | PASS | Risk Management | A3:O17 | Keep ST-09 lessons linked | Closed
Change governance improved | ECNs tie engineering changes to technical and financial disposition | PLM Admin | Monthly | Critical ECN without approval | PASS | Change Management (ECN) | A3:Q18 | Audit ECN approvals | 2026-Q3
External links resolved | Workbook uses local formulas and link prompt status is tracked | PLM Admin | At release | Open update-link prompt | PASS | Dashboard | A4:J10 | Verify on next open | Next open
Operational cadence live | Monthly KPI review plus quarterly steering escalation path | Operations | Monthly / Quarterly | Uptime <96%, cost breach | LIVE | Executive Report | A1:H36 | Use refreshed steering pack | 2026-Q3
PLM data model consistent | Document, BOM, Change, ECN, Validation, Risk and CBA objects aligned | PLM Admin | Quarterly | Broken traceability | PASS | Documents Management | A5:H24 | Refresh Teamcenter export | 2026-Q3
Dashboard Data
MONTHLY PERFORMANCE DATA
Month | Revenue | COGS | Gross Profit | Expenses | Net Profit | Revenue Target | Customers | Avg Order Value
Jan | 285000 | 119700 | 165300 | 95000 | 70300 | 300000 | 142 | 2007.0423
Feb | 310000 | 127100 | 182900 | 98000 | 84900 | 320000 | 155 | 2000
Mar | 340000 | 136000 | 204000 | 102000 | 102000 | 340000 | 170 | 2000
Apr | 325000 | 136500 | 188500 | 100000 | 88500 | 360000 | 163 | 1993.865
May | 365000 | 146000 | 219000 | 105000 | 114000 | 380000 | 182 | 2005.4945
Jun | 390000 | 152100 | 237900 | 108000 | 129900 | 400000 | 195 | 2000
Jul | 375000 | 153750 | 221250 | 106000 | 115250 | 400000 | 188 | 1994.6809
Aug | 410000 | 159900 | 250100 | 112000 | 138100 | 420000 | 205 | 2000
Sep | 425000 | 161500 | 263500 | 115000 | 148500 | 440000 | 213 | 1995.3052
Oct | 450000 | 171000 | 279000 | 118000 | 161000 | 460000 | 225 | 2000
Nov | 470000 | 173900 | 296100 | 120000 | 176100 | 480000 | 235 | 2000
Dec | 520000 | 187200 | 332800 | 125000 | 207800 | 500000 | 260 | 2000
TOTAL | 4665000 | 1824650 | 2840350 | 1304000 | 1536350 | 4800000 | 2333 | 1999.699
EXPENSE BREAKDOWN
Category | Amount | % of Total
Salaries & Wages | 720000 | #DIV/0!
Marketing & Advertising | 180000 | #DIV/0!
Rent & Facilities | 144000 | #DIV/0!
Technology & Software | 96000 | #DIV/0!
Professional Services | 72000 | #DIV/0!
Travel & Entertainment | 48000 | #DIV/0!
Other Operating | 44000 | #DIV/0!
REVENUE BY REGION
Region | Revenue | % of Total
RST-01 | 2680000 | 940.4%
RST-02 | 1180000 | 414%
RST-03 | 620000 | 217.5%
RST-04 | 185000 | 64.91%

## Executive Report
EXECUTIVE REPORT — Full Lifecycle Delivery for Multi-Site Pressure Reducing & Power Generation
Section | Finding / Report Detail | Technical Evidence | Financial Evidence | Operational Evidence | Governance / Escalation | Owner | Status
Executive summary | Portfolio rebuilt as PLM program covering design, validation, commissioning and O&M | Controlled documents, EBOM/MBOM and ECN board rebuilt | Target EPC CapEx $14.0M, payback 5 years, IRR 10–13% | 11 stations operating under KPI review | Monthly ops; quarterly steering | PMO | PASS
Lifecycle ownership | Delivery model is explicitly Project Proposal → Design → Validation & Testing → Commissioning → O&M | Stage-gate sheet maps G0 through G5-FB | Economics tied to gates | O&M release includes uptime controls | Assigned gate owners | PLM Manager | PASS
NPI attrition | 14 candidate stations, 2 filtered before execution, 1 decommissioned after installation, 11 active | Risk sheet lists all 14 stations | Avoided CapEx from removed sites; ST-09 learning captured | Operating count formula-checks to 11 | Reliability board escalation | PMO | PASS
Pre-execution filtering | ST-07 and ST-12 eliminated for site installation risk and physical space constraints | Gate G1 civil envelope checks failed | No stranded execution CapEx | Risks closed before construction | Steering approval | Civil Lead | Closed
Post-install field attrition | ST-09 decommissioned after bearing/vibration failures and failure data fed back to DVP&R | Failure mode linked to validation and risk register | OPEX drag reduced | Reliability monitoring upgraded | Reliability Board | Reliability | Closed
Technical architecture | Station package includes PAT/turbine, generator, bypass valves, stainless pipe spools, MCC/protection, SCADA/historian and instrumentation | BOM includes controlled items and revisions | Reference station MBOM cost summarized | SCADA supports KPI reporting | ECN approvals | Systems Eng. | Released
Pilot program | Pilot captured as $0.75M CapEx, 0.25 MW and 18-month development duration | Pilot closeout and test evidence included | Pilot informs EPC target case | Pilot lessons transferred to design freeze | G3 validation closeout | PMO | Released
Portfolio capacity | 11 operating stations × 0.25 MW average capacity = 2.75 MW operating capacity | Risk station table formulas calculate energy | Generation from capacity × uptime | Uptime aligns to 96–99% KPI | Monthly review | Operations | PASS
Energy and revenue | Annual generation and revenue are calculated from capacity, uptime and $0.175/kWh tariff | CBA bridge transparent | Gross revenue feeds payback and IRR | Revenue metric tied to dashboard | Quarterly finance refresh | Finance | PASS
OPEX model | OPEX includes fixed inspection/compliance plus variable wear/spares and lifecycle reserve | O&M spare kit and reserve in BOM/CBA | OPEX sensitivity visible | Monthly OPEX review controls payback | Steering escalation | O&M / Finance | PASS
Economic hurdle | Target EPC CapEx $14M, payback ≤5 years and IRR 10–13% are embedded as checks | CBA shows formulas and hurdle checks | Payback/IRR surfaced on dashboard | Operating KPIs support durability | Quarterly steering | Finance | PASS
Change management quality | Change log reads like a real technical program from 2012 to 2026 | 24 changes with owners, impacts and dispositions | CapEx/OPEX impacts quantified | Critical changes tracked | Monthly ECN board | PLM Admin | PASS
ECN board | ECN sheet ties changes to item revisions, systems, risk before/after and approvals | Controlled items map to BOM/docs | Financial disposition included | Release states assigned | Design Authority | PLM Admin | PASS
Validation rigor | Validation includes DVP&R, FAT/SAT, overspeed, vibration, protection, bypass and SCADA tests | Acceptance criteria and defects visible | Commercial validation included | Live monitors identified | G3/G4 controls | Validation | PASS
Risk governance | Risk combines site attrition, station data and risk register | Civil, hydraulic, electrical, reliability, cyber and commercial risks included | CapEx/OPEX/tariff risks included | Residual risk status assigned | Quarterly steering | PMO | PASS
Operational reporting | Dashboard includes KPI cards, lifecycle timeline, attrition funnel and actions | Uptime, station count, economics and link status visible | Outputs tie to CBA | Monthly/quarterly cadence stated | Escalate below 96% uptime | Operations | LIVE
Data provenance | Documents sheet uses Teamcenter-like IDs, revisions, release states and owners | Docs align with BOM, ECN and validation objects | User financial targets labeled | Refresh date visible | PLM dictionary included | PLM Admin | PASS
Workbook link remediation | Model rebuilt with local formulas and no visible external references required | Local formulas replace scattered references | Dashboard tracks link-prompt status | Next-open verification recommended | PLM Admin confirm no startup prompt | PLM Admin | PASS
Technical detail | Hydraulic package recovers pressure energy through PAT/generator while preserving bypass function | PAT and bypass controlled in BOM | CapEx included in EPC target | Trips and bypass validated | Engineering change approval | Hydraulics | Released
Technical detail | Electrical design includes generator, MCC, relay protection, metering and grid synchronization | MCC/relay package in ECN board | Grid study cost captured | Trip selectivity validated | Electrical approval | Electrical | Released
Technical detail | Controls include PLC/IO, revenue meter, historian and KPI tag standard | SCADA/historian requirements released | Reporting reduces manual reconciliation | Monthly data QC | Controls / IT-OT | Controls | Released
Technical detail | Mechanical design includes SS316 pipe spools, skid, anchoring, noise, drainage and access | Materials ECN and civil risks included | CapEx quantified | Access failures filtered early | Design Authority | Mechanical | Released
Financial detail | Base case separates EBITDA payback from IRR cash flow after lifecycle reserve | CBA formulas visible | Payback tied to EBITDA; IRR tied to net FCF | Reserve supports O&M | Finance review | Finance | PASS
Financial detail | Sensitivity block gives downside/base/upside tariff and availability context | Scenario table in CBA | Refreshable assumptions | Escalate if IRR below 10% | Quarterly review | Finance | Live
Quality detail | As-built packs, FAT/SAT dossier, HAZOP/LOTO and validation evidence are controlled artifacts | Document and validation registers include owners/dates | No hidden unsourced hardcodes in calculations | O&M release uses evidence | Quality gate | Quality | PASS
Closeout | Workbook now functions as cohesive PLM/Teamcenter-style delivery pack for underground power generation | All primary sheets rebuilt and formatted | Economic targets embedded | Stage-gate and escalation explicit | Ready for steering review | PMO | Complete
Refresh instruction | Update Teamcenter exports quarterly: documents, items, ECNs, station statuses, validation evidence, risks and economics | Structured ranges ready for refresh | Financial inputs centralized | Operating count remains 11 unless status changes | PLM refresh governance | PLM Admin | Open cadence
Escalation rule | Escalate if uptime <96%, payback >5 years, IRR <10%, or critical ECN lacks approval | Dashboard contains trigger fields | CBA contains checks | Operations owner assigned | Monthly/quarterly cadence | PMO | Live
Final QA | No formula errors or visible external workbook formula links found after local formula rebuild; verify startup prompt on next open. | Workbook search/verification follows | CBA and dashboard tie-outs included | Formula checks are visible | Release checklist | PLM Admin | PASS